Project Planning Phase Project Planning Template (Product Backlog, Sprint Planning, Stories, Story Points)

| Date | 28/02/2026 | Team ID | 171 |
| --- | --- | --- | --- |
| Project Name | Quotes Recommendation Chatbot using NLP | Maximum Marks | 5 Marks |

Product Backlog, Sprint Schedule, and Estimation (5 Marks)

Use the below template to create product backlog and sprint schedule:

| Sprint | Functional Requirement (Epic) | User Story Number | User Story / Task | Story Points | Priority | Team Members |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | NLP Core Pipeline | USN-1 | As a user, I can type a natural language message into the chatbot and receive 3 contextually relevant quotes in response. | 3 | High |  |
| Sprint-1 |  | USN-2 | As a developer, the system pre-processes user text using tokenization, stopword removal, and lemmatization via NLTK before passing it to the retrieval engine. | 2 | High |  |
| Sprint-1 |  | USN-3 | As a user, the chatbot detects the emotional tone (positive / negative / neutral) of my message using VADER sentiment analysis and filters quotes accordingly. | 2 | High |  |
| Sprint-1 |  | USN-4 | As a developer, I can load and index 10,000+ quotes from a CSV dataset into a SQLite database with fields: text, author, category, tags, sentiment score. | 2 | Medium |  |
| Sprint-2 | Semantic Matching | USN-5 | As a user, the chatbot understands the meaning behind my message (not just keywords) by encoding it with Sentence-BERT (all-MiniLM-L6-v2) and returning semantically similar quotes. | 3 | High |  |
| Sprint-2 |  | USN-6 | As a developer, all 10,000 quote embeddings are pre-computed offline and stored as a NumPy .npy file so inference latency is under 500ms. | 2 | High |  |
| Sprint-2 |  | USN-7 | As a user, the chatbot uses Faiss approximate nearest-neighbor search to rank and return the top-5 most relevant quotes from the database. | 2 | Medium |  |
| Sprint-3 | Intent Classification & Dialogue | USN-8 | As a user, the chatbot classifies my message intent (motivation / sadness / topic_query / random) using a scikit-learn Logistic Regression model trained on labelled examples. | 3 | High |  |
| Sprint-3 |  | USN-9 | As a user, I can ask for 'a quote by Einstein' and the chatbot uses spaCy NER to detect the author name and filter results accordingly. | 2 | Medium |  |
| Sprint-3 |  | USN-10 | As a user, I can say 'show me more' or 'try a different topic' and the chatbot remembers the previous context and avoids repeating already shown quotes. | 2 | High |  |
| Sprint-4 | Web Interface & Deployment | USN-11 | As a user, I can access the chatbot through a clean web browser chat UI with message bubbles, a typing indicator, and mobile-responsive layout built with Flask + HTML/CSS. | 2 | High |  |
| Sprint-4 |  | USN-12 | As a user, I can save my favourite quotes with a single click and view them in a saved quotes panel during my session. | 1 | Low |  |
| Sprint-4 |  | USN-13 | As a team, the application is deployed to Render / Heroku with Gunicorn and is accessible via a public URL with HTTPS. | 2 | High |  |
| Sprint-4 |  | USN-14 | As a developer, all API endpoints are secured with input sanitization, CORS policy, and rate limiting (Flask-Limiter). | 1 | Medium |  |

Project Tracker, Velocity & Burndown Chart: (5 Marks)

| Sprint | Total Story Points | Duration | Sprint Start Date | Sprint End Date (Planned) | Story Points Completed (as on Planned End Date) | Sprint Release Date (Actual) |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | 12 | 7 Days | 28 Feb 2026 | 06 Mar 2026 | 12 | 06 Mar 2026 |
| Sprint-2 | 7 | 7 Days | 07 Mar 2026 | 13 Mar 2026 |  |  |
| Sprint-3 | 7 | 7 Days | 14 Mar 2026 | 20 Mar 2026 |  |  |
| Sprint-4 | 6 | 7 Days | 21 Mar 2026 | 27 Mar 2026 |  |  |

Velocity: The project has 4 sprints each lasting 7 days (1 week). The total story points across all sprints sum to 32 points. With 4 sprints of 7 days each, the team's Average Velocity (AV) is calculated as story points completed per sprint divided by sprint duration in days. AV = Sprint Story Points / Sprint Duration (days) AV = 8 story points / 7 days ≈ 1.14 story points per day. Total story points: Sprint-1 (12) + Sprint-2 (7) + Sprint-3 (7) + Sprint-4 (6) = 32 story points over 4 weeks. Sprint-1 velocity baseline: 12 points completed in 7 days = 1.71 points/day (includes heavier NLP setup tasks). Remaining sprints (2, 3, 4) average: 6.67 points / 7 days ≈ 0.95 points/day — sustainable delivery pace.

Burndown Chart: A burn down chart is a graphical representation of work left to do versus time. It is often used in agile software development methodologies such as Scrum. Burn down charts can be applied to any project containing measurable progress over time. Burndown Data — Quotes Recommendation Chatbot using NLP (32 Total Story Points) Sprint; Week Ending; Story Points Remaining (Ideal); Story Points Completed; Story Points Actual Remaining; Ideal Burndown Line; Status. Start; 28 Feb 2026; 32; -; 32; 32.0. Sprint-1; 06 Mar 2026; 24; 12; 20; 24.0; Ahead. Sprint-2; 13 Mar 2026; 16; -; -; 16.0. Sprint-3; 20 Mar 2026; 8; -; -; 8.0. Sprint-4; 27 Mar 2026; 0; -; -; 0.0. Visual Burndown (Sprint Story Points Remaining): Story Points Remaining (Y-Axis: 0–32) ¦ Time in Sprints (X-Axis) 32 ¦ ████████████████████████████████ ← Start (28 Feb) 24 ¦ ████████████████████████ ← Ideal after Sprint-1 20 ¦ ████████████████████ ← Actual after Sprint-1 (AHEAD ✓) 16 ¦ ████████████████ ← Ideal after Sprint-2 8 ¦ ████████ ← Ideal after Sprint-3 0 ¦ ← Target completion (27 Mar) ¦______¦______¦______¦______¦ Start Sp-1 Sp-2 Sp-3 Sp-4 Ideal Line: 32 → 24 → 16 → 8 → 0 (8 points/sprint). Actual Line after Sprint-1: 32 → 20 (12 points completed, 4 ahead of ideal).. Reference: https://www.visual-paradigm.com/scrum/scrum-burndown-chart/ Reference: https://www.atlassian.com/agile/tutorials/burndown-charts

Reference:

https://www.atlassian.com/agile/project-management

https://www.atlassian.com/agile/tutorials/how-to-do-scrum-with-jira-software

https://www.atlassian.com/agile/tutorials/epics

https://www.atlassian.com/agile/tutorials/sprints

https://www.atlassian.com/agile/project-management/estimation

https://www.atlassian.com/agile/tutorials/burndown-charts

Quotes Recommendation Chatbot using NLP ¦ Project Planning Phase ¦ Team ID: 171 ¦ 28/02/2026